## Hours Estimation
Man Hour Estimation (Web Application 1 hour = 8USD) (Mobile Application 1 hour = 3 USD)
ACTIVITY | Web Application Man Hours | Android Application Man Hours | iOS Application Man Hours | Total Hours | 10
1. Design & Requirement Analysis | 480
2. Project & Datasource Structuring | 250 | 50 | 50
3. Admin Module
3.1 Admin Menus (Main Page) | 24
3.2 Dashboard | 50
3.3 Admin User List | 10
3.4 Admin User Create/Update Page | 24
3.5 Doctor User List | 10
3.6 Doctor User Create/Update Page | 24
3.7 Patient User List | 10
3.8 Patient User Create/Update Page | 24
3.9 Company List | 10
3.10 Company Create/Update Page | 24
3.11 User Profile Pages | 30
3.12 Change Password | 30
3.13 Picklist list | 30
3.14 Picklist Create/Update Page | 20
3.15 Patient - Medical Insurance Card Info | 20
3.16 Password Management | 30
4. Doctor Module
4.1 Doctor Menus (Main Page) | 24 | 60 | 60
4.2 Dashboard | 100 | 196 | 196
4.3 Appointment
4.3.1 Appointment List Page | 30 | 60 | 60
4.3.2 Patient Details Page | 200 | 390 | 390
4.3.3 Consultation Page(GP) | 64 | 110 | 110
4.3.3 Consultation Page(Specialist) | 400 | 650 | 650
4.3.3 Consultation Page (Allied Health) | 300 | 400 | 400
4.3.4 Patient Examination Page | 200 | 300 | 300
4.4 Messages
4.4.1 Inbox Tab | 16 | 50 | 50
4.4.2 Sent Tab | 16 | 50 | 50
4.4.3 Compose Tab | 16 | 50 | 50
5. Patient Module
5.1 Patient Menus (Main Page) | 24 | 48 | 48
5.2 Dashboard | 50 | 96 | 96
5.3 My Details
5.3.1 Profile | 24 | 72 | 72
5.3.1.1 Step 1: Personal | 24 | 60 | 60
5.3.1.2 Step 2: Address | 24 | 60 | 60
5.3.1.3 Step 3: Contact | 24 | 60 | 60
5.3.1.4 Step 4: Bank Details | 24 | 60 | 60
5.3.1.5 Step 5: Occupation | 24 | 60 | 60
5.3.1.6 Other Remaining Steps | 72 | 120 | 120
5.3.2 My Pharmacy | 10 | 36 | 36
5.4 My Appointments
5.4.1 Future Appointments | 50 | 96 | 96
5.4.2 Past Appointments | 50 | 96 | 96
5.5 Book Appointment
5.5.1 GP | 50 | 96 | 96
5.5.2 Allied Health | 50 | 96 | 96
5.6 My Medical
5.6.1 Request Prescription | 150 | 200 | 200
5.6.2 Pharmacy | 10 | 30 | 30
5.6.3 History | 150 | 150 | 150
5.6.4 My Results | 150 | 150 | 150
Grant Total Hours | 3426 | 3952 | 3952
Total Cost ($) | 27408 | 11856 | 11856
Grant Total Cost($) | 51120
Additonal Task Not Included in Estimation
1. Configuation Management
2. Demo & Deployment
3. Enhancement changes after demo

## Project Planner
Hprovider - Web Application
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | 2017-04-01
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1. Design & Requirement Analysis | 1 | 7 | 1 | 4 | 60%
2. Project & Datasource Structuring | 8 | 5 | 8 |  | 0%
3. Admin Module | 13 | 8 | 13 |  | 0%
3.1 Staging Deployment | 21 | 3 | 21 |  | 0%
3.2 Demo | 23 | 1 | 23 |  | 0%
4. Patient Module - 1 | 24 | 7 | 24 |  | 0%
2017-05-01
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
4. Patient Module - 2 | 1 | 7 | 1 |  | 0%
4.1 Staging Deployment | 8 | 1 | 8 |  | 0%
4.1 Demo | 9 | 1 | 9 |  | 0%
5. Patient Module - 3 | 10 | 16 | 26 |  | 0%
5.1 Staging Deployment | 27 | 1 | 27 |  | 0%
5.2 Demo | 28 | 1 | 28 |  | 0%
2017-06-01
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
6. Patient Module - 3 | 1 | 20 | 1 |  | 0%
6.1 Demo | 21 | 1 | 21 |  | 0%
7. Patient Changes/Enhancements | 22 | 3 | 22 |  | 0%
8. Doctor Module - 1 | 25 | 5 | 25 |  | 0%
8.1 Demo | 26 | 1 | 26 |  | 0%
2017-07-01
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
9. Doctor Module - 2 | 1 | 30 | 1 |  | 0%
9.1 Demo | 31 | 1 | 31 |  | 0%
2017-08-01
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
10. Doctor Module - 3 | 1 | 20 | 1 |  | 0%
10.1 Demo | 21 | 1 | 21 |  | 0%
11. Doctor Changes/Enhancements | 22 | 5 | 22 |  | 0%
Note on B10: Kanniappan Ravichandran Jothilakshmi NCS: Dashbaord, My Details
Note on B13: Kanniappan Ravichandran Jothilakshmi NCS: Book Appointments
Note on B16: Kanniappan Ravichandran Jothilakshmi NCS: My Appointments, My Messages
Note on B21: Kanniappan Ravichandran Jothilakshmi NCS: My Medical & Allied Health functionalities
Note on B24: Kanniappan Ravichandran Jothilakshmi NCS: Dashboard & Profile and Change Password
Note on B28: Kanniappan Ravichandran Jothilakshmi NCS: Appointments
Note on B32: Kanniappan Ravichandran Jothilakshmi NCS: Messages & Others

## ManHours Estimation
ACTIVITY
1. Design & Requirement Analysis
2. Project & Datasource Structuring
3. Admin Module
3.1 Staging Deployment
3.2 Demo
4. Patient Module - 1
4. Patient Module - 2
4.1 Staging Deployment
4.1 Demo
5. Patient Module - 3
5.1 Staging Deployment
5.2 Demo
6. Patient Module - 3
6.1 Demo
7. Patient Changes/Enhancements
8. Doctor Module - 1
8.1 Demo
9. Doctor Module - 2
9.1 Demo
10. Doctor Module - 3
10.1 Demo
11. Doctor Changes/Enhancements
Note on A9: Kanniappan Ravichandran Jothilakshmi NCS: Dashbaord, My Details
Note on A12: Kanniappan Ravichandran Jothilakshmi NCS: Book Appointments
Note on A15: Kanniappan Ravichandran Jothilakshmi NCS: My Appointments, My Messages
Note on A20: Kanniappan Ravichandran Jothilakshmi NCS: My Medical & Allied Health functionalities
Note on A23: Kanniappan Ravichandran Jothilakshmi NCS: Dashboard & Profile and Change Password
Note on A27: Kanniappan Ravichandran Jothilakshmi NCS: Appointments
Note on A31: Kanniappan Ravichandran Jothilakshmi NCS: Messages & Others

## Sheet3
1.Landing Pages
1.1 Main Page
2.Home Page
2.1 Home Section
2.2 About Us Section
2.3 FAQ Section
2.4 Contact us Section
3.Admin
3.1 Admin Menus (Main Page)
3.2 Dashboard
3.3 Admin User List
3.4 Admin User Create/Update Page
3.5 Doctor User List
3.6 Doctor User Create/Update Page
3.7 Patient User List
3.8 Patient User Create/Update Page
3.9 Company List
3.10 Company Create/Update Page
3.11 Organisation
3.12 Organisation Create/Update Page
3.13 Picklist list
3.14 Picklist Create/Update Page
4.Doctor
4.1 Doctor Menus (Main Page)
4.2 Dashboard
4.3 Appointment
4.3.1 Appointment List Page
4.3.2 Patient Details Page
4.3.3 Consultation Page
4.3.4 Patient Examination Page
4.4 Messages
4.4.1 Inbox Tab
4.4.2 Sent Tab
4.4.3 Compose Tab
5.Patient
5.1 Patient Menus (Main Page)
5.2 Dashboard
5.3 My Details
5.3.1 Profile
5.3.1.1 Step 2: Address
5.3.1.2 Step 3: Contact
5.3.1.3 Step 4: Bank Details
5.3.1.4 Step 5: Occupation
5.3.2 My Pharmacy
5.4 My Appointments
5.4.1 Future Appointments
5.4.2 Past Appointments
5.5 Book Appointment
5.5.1 GP
5.5.2 Allied Health
5.6 My Medical
5.6.1 Request Prescription
5.6.2 My Results
6. User Profile Pages
6.1 Change Password